## Sprint Backlog
US ID | Sprint Backlog Item | Task Details | Initial Effort | Status
US01 | Register Driver | Build FastAPI endpoint for driver registration; enforce 18+ age & unique license rules. | 9 | Done
US02 | Register Vehicle | Map vehicle to active driver ID; validate KA-01-AB-1234 state pattern. | 6 | Done
US03 | Record Violation | Inspector-only POST route for violations; map predefined fine amounts. | 9 | Done
US04 | Pay Fine | React UI payment component; prevent partial payments & handle 10% overdue penalty. | 6 | Done
US05 | Renew Road Tax | Ensure active vehicle status; block renewal if unpaid violations exist. | 6 | Done
US06 | Driver Details UI | React view masking license digits; highlight unpaid violations in red. | 6 | Done
US07 | Vehicle Compliance | Display tax status & inspection dates; hide 'stolen' status from public. | 5 | Done
US08 | Expired Licenses | Inspector view; sort by days expired; bulk notice limit logic (max 50). | 5 | Done
US09 | Unpaid Tax List | Group by months overdue; calculate up to 25% max late fee cap. | 5 | Done
US10 | RTO Dashboard | Role-based React dashboard (Clerk: Registrations, Inspector: Compliance). | 7 | Done
US11 | Driver Validation | Backend middleware to check active license status and max 5 vehicle limit. | 4 | Done
US12 | Non-Compliant CRON | Scheduled background task for daily expired tax checks (15-day grace). | 5 | Done
US13 | Late Penalty Logic | 12:01 AM scheduler adding 10% penalty to overdue fines (max 3 times). | 4 | Done
US14 | Invalid License Block | Validation exception handler preventing new violations on expired licenses. | 4 | Done
US15 | Tax Reminders | Automated email alerts at 30, 15, and 5 days before tax expiry. | 5 | Done
US16 | Ownership Validation | API check ensuring vehicle ownership hasn't changed <24 hrs prior. | 4 | Done
US17 | License Deactivation | Auto-deactivate licenses 15 days post-expiry; maintain 1-year history. | 5 | Done
US18 | Storage Backup | Script to migrate deactivated licenses to the archive database table. | 4 | Done
US19 | Role Hierarchy | Three-tier auth (Clerk, Inspector, Superintendent) for renewal approvals. | 6 | Done
US20 | Violation Reports | PDF/Excel generation endpoint for monthly unpaid violation reports. | 7 | Done

## Burndown Chart
Metric | Day 0 | Day 1 | Day 2 | Day 3
Initial Estimation Trend | 108 | 72 | 36 | 0
Actual Estimation Trend | 108 | 75 | 40 | 0