## Sprint Backlog
US ID | Sprint Backlog Item | Task Details | Initial Effort (Hours) | Day 1 (Remaining) | Day 2 (Remaining) | Day 3 (Remaining) | Status
US01 | Driver Management CRUD | Build FastAPI routes & React views to Create, Read, Update, and Delete driver profiles. | 4 | 0 | 0 | 0 | Done
US02 | Vehicle Management CRUD | Full stack CRUD for registering new vehicles, viewing details, updating mapping to drivers, and archiving. | 4 | 0 | 0 | 0 | Done
US03 | Violation Management CRUD | Record new traffic violations, view history, update fine amounts, and delete erroneous challans. | 4 | 0 | 0 | 0 | Done
US04 | Road Tax Management CRUD | Create tax records, view tax compliance status, update payments, and delete invalid entries. | 4 | 0 | 0 | 0 | Done
US05 | License Lifecycle CRUD | Issue new licenses, view license status, update for renewals, and deactivate expired ones. | 4 | 0 | 0 | 0 | Done
US06 | Fine Payment CRUD | Process new payments, view payment history, update transaction status, and handle refunds. | 3 | 3 | 0 | 0 | Done
US07 | Inspector Profile CRUD | Create inspector accounts, view profiles, update roles/permissions, and delete/suspend access. | 3 | 3 | 0 | 0 | Done
US08 | Clerk Profile CRUD | Manage RTO clerk accounts (Create, Read, Update, Delete) for daily administration tasks. | 3 | 3 | 0 | 0 | Done
US09 | Ownership Transfer CRUD | Initiate transfer, view transfer history, update ownership status, and cancel requests. | 3 | 3 | 0 | 0 | Done
US10 | Driving Test Slots CRUD | Create test schedules, view available slots, update bookings, and cancel appointments. | 3 | 3 | 0 | 0 | Done
US11 | Emission (PUC) CRUD | Record new pollution certificates, view validity, update status, and delete expired records. | 3 | 3 | 0 | 0 | Done
US12 | Insurance Record CRUD | Add insurance policies, view coverage details, update renewals, and remove invalid policies. | 3 | 3 | 1 | 0 | Done
US13 | Commercial Permit CRUD | Issue transport permits, view commercial status, update validities, and revoke permits. | 3 | 3 | 3 | 0 | Done
US14 | RC Book Management CRUD | Generate RC print requests, view printing status, update dispatch details, and cancel. | 3 | 3 | 3 | 0 | Done
US15 | Notification System CRUD | Create alert templates, view sent logs, update notification settings, and delete old logs. | 3 | 3 | 3 | 0 | Done
US16 | RTO Branch Management CRUD | Add new regional offices, view branch details, update locations, and close branches. | 3 | 3 | 3 | 0 | Done
US17 | Audit Log Management CRUD | System generated: Read and View system audit logs, export logs, and archive old data. | 3 | 3 | 3 | 0 | Done
US18 | Dispute Resolution CRUD | File citizen disputes, view dispute status, update resolutions, and close cases. | 3 | 3 | 3 | 0 | Done
US19 | Camera API Webhooks CRUD | Register traffic camera endpoints, view telemetry, update connections, and delete nodes. | 3 | 3 | 3 | 0 | Done
US20 | Analytics Reports CRUD | Create report configurations, view generated stats, update dashboard widgets, and delete templates. | 3 | 3 | 3 | 0 | Done
|  | Total Remaining Hours: | 65 | 45 | 25 | 0

## Burndown Chart
Metric | Day 0 | Day 1 | Day 2 | Day 3
Initial Estimation Trend | 65 | 43.5 | 22 | 0
Actual Estimation Trend | 65 | 45 | 25 | 0