## Defect Log
Defect ID | Description | Steps | Actual | Expected | Severity | Priority | Raised By | Date | Assigned To | Root Cause | Fix | Status
D-01 | Underage driver registered | Register age<18 | Registered | Reject | High | High | Tester | 29-Jun | Dev1 | Age validation missing | Added check | Closed
D-02 | Duplicate license allowed | Reuse license | Accepted | Unique license | High | High | Tester | 29-Jun | Dev1 | Unique validation missing | Fixed | Closed
D-03 | Expired license violation | Add violation | Created | Reject | High | High | Tester | 30-Jun | Dev2 | License check missing | Fixed | Closed
D-04 | Partial payment accepted | Pay half amount | Accepted | Full payment | Medium | High | Tester | 30-Jun | Dev2 | Payment check | Fixed | Closed
D-05 | RBAC issue | Clerk access inspector | Allowed | Denied | Critical | High | Tester | 01-Jul | Dev3 | Role validation | Fixed | Closed