## Quality Log
ID | Review Date | Deliverable Reviewed | Required Findings | Actual Findings | Resolution | Sign Off
QL-01 | 29-Jun | Authentication Module | Role login works | Login validated | Approved | Scrum Master
QL-02 | 29-Jun | Driver Registration | Age/license validation | Validation issue found | Fixed | Scrum Master
QL-03 | 29-Jun | Vehicle Registration | Driver ownership verified | Passed | Approved | Scrum Master
QL-04 | 30-Jun | Violation Module | Violation rules enforced | License validation missing | Fixed | Scrum Master
QL-05 | 30-Jun | Payment Module | Full payment enforcement | Passed | Approved | Scrum Master
QL-06 | 30-Jun | Tax Module | Renewal rules | Penalty issue found | Fixed | Scrum Master
QL-07 | 01-Jul | Dashboard | Role metrics correct | Passed | Approved | Scrum Master
QL-08 | 01-Jul | Reports | Monthly reports accurate | Passed | Sprint Signoff | Scrum Master