## Sprint Backlog
US | Module | Task | Initial Effort(Hrs) | Day1 Remaining | Day2 Remaining | Day3 Remaining | Status
US01 | Driver | Create Driver API | 3 | 2 | 1 | 0 | Done
US01 | Driver | Driver Registration | 4 | 3 | 1 | 0 | Done
US01 | Driver | License Validation | 2 | 1 | 0 | 0 | Done
US02 | Vehicle | Vehicle Registration | 4 | 3 | 1 | 0 | Done
US02 | Vehicle | Reg Number Validation | 2 | 1 | 0 | 0 | Done
US03 | Violation | Record Violation | 4 | 3 | 1 | 0 | Done
US03 | Violation | Fine Calculation | 2 | 1 | 0 | 0 | Done
US04 | Payment | Fine Payment | 3 | 2 | 1 | 0 | Done
US05 | Tax | Road Tax Renewal | 3 | 2 | 1 | 0 | Done
US06 | Driver | View Driver Details | 2 | 1 | 0 | 0 | Done
US07 | Vehicle | View Vehicle Details | 2 | 1 | 0 | 0 | Done
US08 | License | Expired License Report | 2 | 1 | 0 | 0 | Done
US09 | Tax | Unpaid Tax Report | 2 | 1 | 0 | 0 | Done
US10 | Dashboard | Role Dashboard | 3 | 2 | 1 | 0 | Done
US11 | Validation | Driver Validation | 2 | 1 | 0 | 0 | Done
US12 | Compliance | Non-Compliant Vehicle | 2 | 1 | 0 | 0 | Done
US13 | Penalty | Late Penalty Logic | 2 | 1 | 0 | 0 | Done
US14 | Validation | Invalid License Restriction | 2 | 1 | 0 | 0 | Done
US15 | Reminder | Tax Reminder Service | 2 | 1 | 0 | 0 | Done
US16 | Validation | Ownership Validation | 2 | 1 | 0 | 0 | Done
US17 | License | Auto Deactivation | 2 | 1 | 0 | 0 | Done
US18 | Archive | Archive Drivers | 2 | 1 | 0 | 0 | Done
US19 | Security | RBAC Access | 3 | 2 | 1 | 0 | Done
US20 | Reports | Monthly Violation Report | 3 | 2 | 1 | 0 | Done